## Roadmap to V1
Nigeria Finance App — Build Tracker (Path to Version 1)
Update the Status column as work progresses. P0 = must-have for V1, P1 = should-have, P2 = nice-to-have / can slip.
ID | Phase | Feature Area | Task / Deliverable | Description | Priority | Status | Depends On | Notes
0.1 | 0 | Setup | Repo & frontend scaffolding | Initialize Next.js app; run shadcn/ui init with the agreed preset (b8Qy9QDHYe, --pointer) | P0 | Not Started | - | Foundation for all frontend work
0.2 | 0 | Setup | Backend scaffolding | Initialize Node.js/Express (or NestJS) API project, folder structure, env config | P0 | Not Started | -
0.3 | 0 | Setup | Database schema & migrations | Postgres schema for users, transactions, categories, budgets, goals; migration tooling | P0 | Not Started | 0.2
0.4 | 0 | Setup | Queue infrastructure | Redis + BullMQ setup for background jobs | P0 | Not Started | 0.2
0.5 | 0 | Setup | Object storage | S3-compatible bucket for receipt images/PDFs | P0 | Not Started | 0.2
0.6 | 0 | Setup | Deployment pipeline | Basic CI/CD + staging environment | P1 | Not Started | 0.1, 0.2
1.1 | 1 | Auth | Phone OTP auth | Integrate Termii/Africa's Talking for signup/login via phone number | P0 | Not Started | 0.2, 0.3
1.2 | 1 | WhatsApp | Business API setup | Meta business verification, BSP account (Termii/360dialog), dedicated number | P0 | Not Started | - | Approval process takes time — start this early, in parallel with 0.x
1.3 | 1 | WhatsApp | Webhook receiver | Handle inbound image/PDF messages, resolve WhatsApp media URLs, download to storage | P0 | Not Started | 1.2, 0.4
1.4 | 1 | WhatsApp | Account linking | Map WhatsApp sender number to app user account | P0 | Not Started | 1.1, 1.3
1.5 | 1 | Ingestion | In-app upload (fallback) | Manual upload flow for users without the bot linked | P1 | Not Started | 0.5
1.6 | 1 | OCR | OCR provider integration | Google Cloud Vision or AWS Textract integration | P0 | Not Started | 0.4, 0.5
1.7 | 1 | OCR | PDF text extraction | Direct text extraction for PDF receipts; OCR fallback if no text layer | P0 | Not Started | 1.6
1.8 | 1 | Parsing | Bank template registry | Parser templates for 3–4 priority banks/fintechs (e.g. GTBank, Kuda, OPay, Access) | P0 | Not Started | 1.6, 1.7
1.9 | 1 | Parsing | Categorization engine | Rule-based merchant-to-category mapping | P0 | Not Started | 1.8
1.10 | 1 | Parsing | Dedup logic | Hash-based duplicate detection (amount, date, reference number) | P1 | Not Started | 1.8
1.11 | 1 | WhatsApp | Bot confirmation replies | Bot replies in-chat with parsed transaction, or asks for correction on low confidence | P0 | Not Started | 1.4, 1.9
1.12 | 1 | UI | Dashboard screen | Transaction feed + spend overview (shadcn: card, table, tabs, badge, skeleton) | P0 | Not Started | 0.1
1.13 | 1 | UI | Transaction confirm/correct screen | Review & fix low-confidence extractions (shadcn: dialog/sheet, form, select) | P0 | Not Started | 1.12, 1.9
1.14 | 1 | UI | Onboarding / auth screens | Phone verification + WhatsApp linking UI (shadcn: form, input-otp) | P0 | Not Started | 1.1, 1.4
1.15 | 1 | UI | Settings screen | WhatsApp link status, notification preferences | P1 | Not Started | 1.12
1.16 | 1 | Sync | Dashboard live updates | Polling (MVP) or WebSocket/SSE + toast when a new transaction lands | P1 | Not Started | 1.12
2.1 | 2 | Budgets | Budgets CRUD API | Create / edit / delete category budgets | P0 | Not Started | 0.3
2.2 | 2 | Budgets | Threshold alerts | Alert when spend nears/exceeds a budget limit (e.g. 80%) | P1 | Not Started | 2.1
2.3 | 2 | Budgets | Budgets UI | List, create/edit form, progress bars (shadcn: progress, card, form, alert) | P0 | Not Started | 2.1
2.4 | 2 | Goals | Goals CRUD API | Create / edit / delete savings & investment goals | P0 | Not Started | 0.3
2.5 | 2 | Goals | Goal progress tracking | Manual contribution logging + progress calculation | P0 | Not Started | 2.4
2.6 | 2 | Goals | Goals UI | List, create/edit form, progress + target date (shadcn: progress, card, form, calendar) | P0 | Not Started | 2.4
2.7 | 2 | Planning | Spend projection | Projected month-end spend based on current pace | P2 | Not Started | 2.1 | Nice-to-have, can slip past V1
2.8 | 2 | Notifications | In-app budget/goal alerts | Toast/badge alerts for budget thresholds and goal milestones | P1 | Not Started | 2.2, 2.5
▲ V1 LAUNCH CHECKPOINT — everything above this line is in scope for Version 1 ▲
3.1 | 3 | Mobile | Capacitor wrap | Wrap the web app with Capacitor for iOS/Android | P1 | Not Started | - | Post-V1
3.2 | 3 | Mobile | Native share target | Android intent filter + iOS share extension for direct receipt sharing | P1 | Not Started | 3.1 | Post-V1
3.3 | 3 | Mobile | Push notifications (native) | Native push for budget/goal alerts | P1 | Not Started | 3.1, 2.8 | Post-V1
3.4 | 3 | Mobile | App store submission | iOS App Store + Google Play listing and review | P1 | Not Started | 3.1, 3.2 | Post-V1
B.1 | B | Backlog | Email / Gmail scraping | OAuth Gmail/Outlook, scheduled bank-alert email sync | P2 | Not Started | - | Deferred per scope decision — revisit after V1
B.2 | B | Backlog | Open banking integration | Mono/Okra direct account aggregation | P2 | Not Started | - | Could reduce reliance on OCR accuracy
B.3 | B | Backlog | ML categorization upgrade | Replace/augment rule-based categorization with a trained classifier | P2 | Not Started | 1.9 | Needs labeled data accumulated from Phase 1 usage

## Summary
Progress Summary
Counts update automatically from the Roadmap to V1 sheet.
By status (all tasks)
Status | Count
Not Started | 37
In Progress | 0
Done | 0
Blocked | 0
Total tasks | 37
% Done | 0%
By phase — V1 scope only (Phase 0, 1, 2)
Phase | Total | Done
Phase 0 — Setup | 6 | 0
Phase 1 — Receipt Ingestion & Dashboard | 16 | 0
Phase 2 — Budgeting & Goals | 8 | 0